## Sheet1
Risk ID | Risk Name | Description | Probability | Impact | Risk Factor | Mitigation | Responsible | Follow Up Date | Status Date | Status | (scale 5=high, 1=low)
A4 | Improper Requirements | Creating poor project requirements between the front-end and backend teams | 3 | 5 | 15 | Group Meetings between front + back - end teams. Consistent communication as the schema, and models are defined | Diana |  | 25-10-2018 | Initial
A1 | Lack of Team Power | Not having enough input from team members (shortage of manpower) | 3 | 4 | 12 | Group communication, task management / allocation | Colin |  | 25-10-2018 | Initial
A3 | Low Code Quality | Code that is not sustainable, and hard to maintain | 3 | 4 | 12 | Code reviews, Cross pollination (Front-end review back-end) | Alexia |  | 25-10-2018 | Initial
B2 | Lack of Node Knowledge | Not all members have worked with Node / Express.js | 3 | 4 | 12 | Pair Programming, code reviews with Dan, and Online tutorials | Dan |  | 25-10-2018 | Initial
B1 | Delete Database | Someone accidentally drops the production database | 2 | 5 | 10 | Do not allow DB:drop on production tables | Dan |  | 25-10-2018 | Initial
W1 | Lack of React Experience | Not all members are comfortable in React | 2 | 4 | 8 | Pair Programming, simple tasks, online resources | Colin |  | 25-10-2018
A2 | Test Environment Not Ready | Build the app, but no test environmnet when ready to write unit tests | 1 | 3 | 3 | Create Test env EARLY | Mircea |  | 25-10-2018 | Initial
[5 empty] | 0 |  |  |  | 25-10-2018
[5 empty] | 0 |  |  |  | 25-10-2018
0
0
0
0
0
0
0
0
0